Guideline of ISAAC organization

1. Concept

- Symposium chair is the person to take responsibility and leadership.

- Symposium organizers and Ad Com should try to obtain good public-evaluation and satisfaction of participants to maintain reputation of ISAAC.

- Arrangement with early preparation and kind information is requested

- Advisory Committee will tell experience of past ISAAC and help organizers.

- Therefore, the symposium chair should keep in touch with the Ad Com chair.

2. Typical schedule of ISAAC n

- Initial proposal:  Early (say, before April) in the year n-2.

- Presentations of proposal and decision: Ad com meeting at ISAAC n-2.

  - Required information: Conference chair, PC chair, venue, dates, accommodation, and idea of finance.

- PC+OC organization, financial plan, hotel negotiation (in year n-1)

- Presentation at ISAAC n-1 Ad com and banquet.

- Symposium Web page open , get an Easychair account(January n)

- Contact to LNCS (March n)

- Preliminary CFP release to major theory mailing list (March/April n)

- Submission open (May n), Final CFP (xx – 10, June n)

- Paper submission deadline  (xx June n)

- Notification  (yy  August n) , report to LNCS

- Best paper selection  (August n)

- Registration/Accommodation open (September n)

- Camera ready handling, Send to Springer (September n)

- Local arrangement work (Oct – Dec n)

- Symposium (December n)

3. Details

3-1． Proposal

- A proposal of ISAAC symposium should be sent to Advisory Committee through one of the committee members in the year n-2 (say, before April).

- The proposal should contain the following information

  - Symposium Chair

  - PC chair (co-chairs)

  - Location (city)

  - Date ( candidate dates)

  - Candidate of site and accommodation plan

  - Conference organization (local arrangement plan)

  - Financial plan (estimated registration fee, possibility of additional funding)

- Final candidate proposal is given at the Advisory Committee meeting at ISAAC n-2.

3-2. Symposium organization

- At ISAAC n-1, the symposium plan of ISAAC n should be presented by the symposium chair (or a deputy) in both advisory committee meeting and banquet.

- Preliminary CFP should be shown at ISAAC (n-1) advisory committee meeting.

  - Ad Com should hear about details such as paper submission guideline, finance, payment systems and local arrangement status.

3-3. Symposium Web

- Symposium Chair should prepare a conference web as soon as possible after the ad com meeting of ISAAC n-1

- Information should be posted timely (as early as possible)

  - Dates, submission information, symposium site, travel, invited speakers.

- Substantial change of the plan should be informed to Ad Com in advance.

3-4. Program Committee

- PC Chair should be assigned early (usually before ISAAC n-2).

- PC Chair should select (most of) PC members before ISAAC n-1

- PC members cannot be a coauthor of a submission to ISAAC

- PC should do substantial discussion (online discussion) for the paper selection.

  - Scores are just data for the discussion.

  - Final decision should be done by PC chairs

  - PC chairs may remove junk papers before the paper assignment

3-5.  Proceedings

- ISAAC proceedings are published by LNCS, unless Ad Com decides otherwise.

  - Symposium chair should send request email to Springer

    - Alfred Hofmann (alfred.hofmann “at“ springer.com)

    - Anna Kramer (anna.kramer ”at” springer.com), lncs@springer.com

  - Maximum limit: 1350 pages (including front+ backmatter)

- Page length and format of the final version should be given in the conference WEB before the acceptance notification.

3-6.  Finance

- Plan the finance carefully

  - Keep low registration (student registration) fee

  - Please consider and try possible additional funding source

- Prepare convenient payment system ( It is often expensive)

- We do not allow a “no-show” paper, thus should omit a paper from the proceedings unless at least one author registers (symposium chair may allow cancellation of a talk by his/her decision).  Traditionally, we allow a person to present more than one paper with single registration fee (student fee, if he/she is a student).

3.7  Communication

- Communication with participants should be done by a responsible person in OC who can quickly respond by his/her own responsibility.

- Symposium chair can consult Ad Com chair anytime.